## Milestones
Milestone | Start date | % Complete | Target End Date | Completion Date | Date Revisions | Status | Comments
Research and Choose Reader's Workshop Teacher Materials
Order samples | 2015-07-14 | 100% | 2015-09-30 | 2015-09-18 |  | 3
Review samples | 2015-09-29 | 33% | 2015-10-06 |  |  | 3
Possible pilots with a specific purpose | 2015-09-29 |  | 2015-10-30 |  |  | 3
3
Visualizing the Reader's Workshop Classroom
Share and watch video | 2015-08-10 |  | 2015-09-29 |  | TBD | 3 | not sure teachers want to do this
Schedule school visits: admin & tchrs | 2015-08-10 |  | 2015-09-09 |  | TBD | 3 | not sure teachers want to do this
3
Classroom Libraries
Service club grants | 2015-09-15 |  | 2015-10-15 |  |  | 3 | Jayne's dates and set meeting
Individual titles | 2015-11-02 |  | 2016-02-19 |  |  | 3
Gudied reading sets | 2015-11-02 |  | 2016-02-19 |  |  | 3
Order materials | 2015-03-01 |  | 2016-03-31 |  |  | 3
Organize materials | 2015-06-23 |  | 2016-08-12 |  |  | 3
Deliver materials | 2016-08-15 |  | 2016-08-19 |  |  | 3
Classroom furniture
Develop furniture inventory list | [5 empty] | 3
Inventory current classrooms | 2016-02-01 |  | 2016-02-26 |  |  | 3
Determine budget and need gap | 2016-02-29 |  | 2016-03-31 |  |  | 3
Plan for gap - now and future orders | 2016-02-29 |  | 2016-03-31 |  |  | 3
Order shelves and ?? | 2016-04-11 |  | 2016-05-13 |  |  | 3
Professional development
Schedule August 2016 reading PD | 2016-02-01 |  | 2016-03-31 |  |  | 3
Hire embedded PD for 2016-17 | 2016-03-01 |  | 2016-03-31 |  |  | 3
August PD | 2016-08-22 |  | 2016-08-25
Surplus plans | [5 empty] | 3
Plan surplus | 2016-04-11 |  | 2016-04-29 |  |  | 3

## Project Plan
August | September | October | November | December | January | February | March | April | May | June | July | August | September
Order samples | Convene cmtte - review scope of work 9/28 | Mtg: Analyze materials Oct 6, 20, 27 | Mtg: Analyze materials Date | Mtg: Select materials Date | IMC meeting
Research videos | Mtg: Review materials & decide on pilots - if any 9/28 | Pilots if needed | Pilots if needed | Sub cmtte: furniture list Date | Survey inventory to teachers Date | Develop priorized furniture list w/ costs | Furniture in budget process | Determine gap and long term plan
Schedule school visits |  | Visit schools TBD - if needed |  |  | School board mtg January 28th
| Service club grants for classroom libraries | Sub cmttee: choose titles Oct - Dec | Sub cmttee: choose titles Oct - Dec | Sub cmttee: choose titles Oct - Dec
[5 empty] | Contract PD |  | August 22-25 PD