Professional Development Planning Timeline

	 1
	Course proposal (need dates, time & location)
	6 weeks prior to event

	2
	Find facility or book meeting room

· P.O. for facility rental if needed
	6 weeks prior to event

	3
	Cost out class
	6 weeks prior to event

	4
	If applicable, send presenter NWESD Presenter Orientation
	6 weeks prior to event

	5
	Clock hours - takes 2 weeks to get approval from PDCC
	6 weeks prior to event

	6
	SPU Credit
	6 weeks prior to event

	7
	Go Sign Me Up
	6 weeks prior to event

	8
	Contract Process:

1. Position Analysis (if needed)

2. ICA Qualifier

3. Purchase order (may need bids)

4. Write contract

5. Internal approvals

6. Contractor approval

7. Superintendent approval, mail to presenter
	6 weeks prior to event

	9
	Copyright permission
	3 weeks prior to event

	10
	Food Form (need P.O.)
	2 weeks prior to event

	11
	Order participant consumable supplies (need P.O.)
	2 weeks prior to event

	12
	Copies / Prep for class
	1 week prior to event

	13
	Sub reimbursement (need P.O.)
	1 week prior to event

	14
	Cancel class if low enrollment

· Cancel purchase orders

· Cancel clock hours / SPU credits

· Cancel instructor (ICA)

· Cancel room

· Cancel or transfer participants (refunds)
	1 week prior to event


6/27/14


